## CAD
Date/Time: | 2022-06-23 16:15 |  | Status: | Empty | Open | Approved | No agreement | Waiting for response from STIHL | Pre-confirmed
Sums: |  |  |  |  | 73134.7 | 41844.37 | 31290.33 | 4519 | 26771.33 |  | 6459.88 | 6601.42 | 8328.16 | 7369.92 | 8561.95 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project name | E-Nr | S-Nr | PJM-CZ | PJM-DE | Ordered | Used | Available | Planned | Not planned | Note | 2022 January | 2022 February | 2022 March | 2022 April | 2022 May | 2022 June | 2022 July | 2022 August | 2022 September | 2022 October | 2022 November | 2022 December
Projekt 1 | E-19300001 | S-22-0001-T01 | Tonda | Uwe | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projekt 2 | E-19300002 | S-22-0002-T01 | Alois | Georg | 197.9 | 139.86 | 58.04 | 0 | 58.04 |  |  | 4.67 | 6.05 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projekt 3 | E-19300003 | S-22-0003-T01 | Jakub | Andreas | 0 | 0 | 0 | 0 | 0 |  | 15.75 | 8.4 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projekt 4 | E-19300004 | S-22-0004-T01 | Richard | Tobias | 346.1 | 345.79 | 0.31 | 0 | 0.31 |  | 45.05 | 61.2 | 20.97 |  | 200 |  | 0 | 0 | 0 | 0 | 0 | 0
Projekt 5 | E-19300005 | S-22-0005-T01 | Míra | Marcel | 97.4 | 81.8 | 15.6 | 0 | 15.6 |  | 36.11 | 28.9 | 6.25 |  | 250 |  | 0 | 0 | 0 | 0 | 0 | 0
Note on M6: <b>Status:</b> Freigegeben <b>User:</b> Jiří Schmidt [2022-03-11 13:08:20] <b>Order:</b> <i>B-Nr[4520451440]</i> = 4.67Std.<span style="color:#00e600;">(67.61%)</span> <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-03-04 17:29:59] <b>Final:</b> ->4.67
Note on N6: <b>Status:</b> Freigegeben <b>User:</b> Jiří Schmidt [2022-04-19 08:59:43] <b>Order:</b> <i>B-Nr[4520451440]</i> = 6.05Std.<span style="color:#00e600;">(70.67%)</span> <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-04-06 14:00:07] <b>Final:</b> ->6.05
Note on L7: <b>Status:</b> Freigegeben <b>User:</b> Petr Pasek [2022-02-10 15:35:40] <b>Order:</b> <i>B-Nr[4520543178]</i> = 15.75Std.<span style="color:#00e600;">(95.78%)</span> abgestimmt mit Herrn Heinzelmann <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-02-08 12:57:16] <b>Final:</b> ->15.75
Note on M7: <b>Status:</b> Freigegeben <b>User:</b> Petr Pasek [2022-03-14 07:44:24] <b>Order:</b> <i>B-Nr[4520543178]</i> = 8.40Std.<span style="color:#00e600;">(100.00%)</span> abgestimmt mit Frau Haas <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-03-04 17:34:45] <b>Final:</b> ->8.4
Note on L8: <b>Status:</b> Freigegeben <b>User:</b> Zbysek Balvin [2022-02-09 12:54:35] <b>Order:</b> <i>B-Nr[4520543793]</i> = 45.05Std.<span style="color:#00e600;">(76.17%)</span> E-Mail vom 9.2.2022 <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-02-08 12:59:24] <b>Final:</b> ->45.05
Note on M8: <b>Status:</b> Freigegeben <b>User:</b> Zbysek Balvin [2022-03-08 09:26:48] <b>Order:</b> <i>B-Nr[4520543793]</i> = 61.20Std.<span style="color:#00e600;">(93.85%)</span> E-Mail vom 8.3.2022 <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-03-04 17:36:19] <b>Final:</b> ->61.20
Note on N8: <b>Status:</b> Freigegeben <b>User:</b> Zbysek Balvin [2022-04-08 14:13:54] <b>Order:</b> <i>B-Nr[4520543793]</i> = 20.97Std.<span style="color:#00e600;">(99.91%)</span> E-Mail vom 8.4.2022 <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-04-06 14:15:58] <b>Final:</b> ->20.97
Note on L9: <b>Status:</b> Freigegeben <b>User:</b> Zbysek Balvin [2022-02-09 12:48:02] <b>Order:</b> <i>B-Nr[4520545054]</i> = 36.11Std.<span style="color:#00e600;">(47.90%)</span> E-Mail vom 9.2.2022 <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-02-08 13:01:48] <b>Final:</b> ->36.11
Note on M9: <b>Status:</b> Freigegeben <b>User:</b> Zbysek Balvin [2022-03-07 12:48:02] <b>Order:</b> <i>B-Nr[4520545054]</i> = 28.90Std.<span style="color:#00e600;">(77.57%)</span> E-Mail vom 7.3.2022 <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-03-04 17:38:11] <b>Final:</b> ->28.9
Note on N9: <b>Status:</b> Freigegeben <b>User:</b> Zbysek Balvin [2022-04-11 14:05:17] <b>Order:</b> <i>B-Nr[4520545054]</i> = 6.25Std.<span style="color:#00e600;">(83.98%)</span> E-Mail vom 11.4.2022 (Stark, vertretet Karl) <b>Status:</b> Leer <b>User:</b> Veronika Makaskova [2022-04-06 14:17:06] <b>Final:</b> ->6.25

## FEM
|  |  | Status: | Empty | Open | Approved | No agreement | Waiting for response from STIHL | Pre-confirmed
Sums: |  |  |  |  | 11756.7 | 7440.91 | 4315.79 | 0 | 4315.79 |  | 1211.69 | 1308.53 | 1455.4 | 1036.84 | 1488.85 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project name | E-Nr | S-Nr | PJM-CZ | PJM-DE | Ordered | Used | Available | Planned | Not planned | Note | 2022 January | 2022 February | 2022 March | 2022 April | 2022 May | 2022 June | 2022 July | 2022 August | 2022 September | 2022 October | 2022 November | 2022 December

## CFD
Date/Time: | 2022-06-23 16:15 |  | Status: | Empty | Open | Approved | No agreement | Waiting for response from STIHL | Pre-confirmed
Sums: |  |  |  |  | 8078.07 | 5363.77 | 2714.3 | 0 | 2714.3 |  | 1043.68 | 826.17 | 903.24 | 862.36 | 1194.92 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project name | E-Nr | S-Nr | PJM-CZ | PJM-DE | Ordered | Used | Available | Planned | Not planned | Note | 2022 January | 2022 February | 2022 March | 2022 April | 2022 May | 2022 June | 2022 July | 2022 August | 2022 September | 2022 October | 2022 November | 2022 December